## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
Python Weather App
Alpha Sapiens
CSCI 5828
Project start date: | 2023-03-09 |  |  |  |  | March | [27 empty] | April
Scrolling increment: | 0 | time axis 2023-03-09 to 2023-05-03
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-09 to 2023-05-03
Project Start
Project Start | Milestone |  |  | 2023-03-16 | 1 | bar: 2023-03-16
Web App Deployment
Simple Form Deployment | On Track |  | 100% | 2023-03-16 | 7
User Interface
Create User | On Track |  |  | 2023-03-23 | 3
User Login/Logout | On Track |  |  | 2023-03-23 | 3
Update Username/Password | On Track |  |  | 2023-03-26 | 3
Upgrade/Downgrade User | On Track |  |  | 2023-03-26 | 3
Specify weather location | On Track |  |  | 2023-03-26 | 3
Display Current Weather | On Track |  |  | 2023-03-29 | 4
Display Warnings/Advisories for Locations | On Track |  |  | 2023-03-29 | 4
Favorite/Un-Favorite Weather Locations | On Track |  |  | 2023-03-29 | 4
Convert from English to Metric | On Track |  |  | 2023-04-02 | 3
Customize Homepage | On Track |  |  | 2023-04-05 | 10
Share weather Information | On Track |  |  | 2023-04-15 | 5
Data Collector
Get Current Location | On Track |  |  | 2023-03-22 | 4
NOAA API Current Weather Interface | On Track |  |  | 2023-03-22 | 4
NOAA API Forecast Interface | On Track |  |  | 2023-03-22 | 4
NOAA API Past Weather Interface | On Track |  |  | 2023-03-22 | 4
NOAA API Advisory/Warning Interface | On Track |  |  | 2023-03-22 | 4
Data Analyzer
Plot Previous Weather Data | On Track |  |  | 2023-03-26 | 7
Database
User Login Information | On Track |  |  | 2023-03-26 | 3
User Free/Premium Acct Info | On Track |  |  | 2023-03-29 | 3
User Configuration Information (Acct type, metric/english, favorites, default information) | On Track |  |  | 2023-04-01 | 10
Final Presentation
Final Presentation | Milestone |  |  | 2023-04-20 | 1 | bar: 2023-04-20
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Dark
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Gupreet Bawa
Project start date: | 2023-03-20 |  |  |  |  | March | [6 empty] | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2023-03-25 to 2023-05-19
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
TITLE 1
Task 1 | Goal | Name | 25% | 2023-03-20 | 3
Task 2 | Milestone |  |  | 2023-03-25 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2023-03-17 | 10
Task 4 | Milestone |  |  | 2023-04-09 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2023-03-26 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-03-26 | 13
Task 2 | On Track |  | 50% | 2023-03-28 | 9
Task 3 | Low Risk |  | 33% | 2023-04-02 | 11
Task 4 | Milestone |  |  | 2023-04-04 | 1 | bar: T
Task 5 |  |  |  | 2023-04-05 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-04-04 | 4
Task 2 | Med Risk |  |  | 2023-04-07 | 14
Task 3 | On Track |  |  | 2023-04-22 | 6
Task 4 | Goal |  |  | 2023-04-26 | 3 | W: 2; T: 2; F: 2
Task 5 | Low Risk |  |  | 2023-03-26 | 19
TITLE 4
Task 1 |  |  |  | 2023-04-29 | 15
Task 2 |  |  |  | 2023-05-13 | 5
Task 3 | Milestone |  |  | 2023-06-24 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2023-03-20 |  |  |  |  | March | [6 empty] | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2023-03-25 to 2023-05-19
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2023-03-25 to 2023-05-19
TITLE 1
Task 1 | Goal | Name | 25% | 2023-03-20 | 3
Task 2 | Milestone |  |  | 2023-03-25 | 1 | bar: 2023-03-25
Task 3 | Low Risk |  | 50% | 2023-03-17 | 10
Task 4 | Milestone |  |  | 2023-04-09 | 1 | bar: 2023-04-09
Task 5 | Med Risk |  | 10% | 2023-03-26 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2023-03-26 | 13
Task 2 | On Track |  | 50% | 2023-03-28 | 9
Task 3 | Low Risk |  | 33% | 2023-04-02 | 11
Task 4 | Milestone |  |  | 2023-04-04 | 1 | bar: 2023-04-04
Task 5 |  |  |  | 2023-04-05 | 24
TITLE 3
Task 1 | On Track |  |  | 2023-04-04 | 4
Task 2 | Med Risk |  |  | 2023-04-07 | 14
Task 3 | On Track |  |  | 2023-04-22 | 6
Task 4 | Goal |  |  | 2023-04-26 | 3 | 2023-04-26: 2; 2023-04-27: 2; 2023-04-28: 2
Task 5 | Low Risk |  |  | 2023-03-26 | 19
TITLE 4
Task 1 |  |  |  | 2023-04-29 | 15
Task 2 |  |  |  | 2023-05-13 | 5
Task 3 | Milestone |  |  | 2023-06-24 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one